pdf_options:
  margin:
    top: 30mm
    bottom: 25mm
    left: 22mm
    right: 22mm
  displayHeaderFooter: true
  headerTemplate: "<span></span>"
  footerTemplate: "<div style='font-size:9px; color:#8a7e72; width:100%; text-align:center; padding:0 40px;'>Familiar Guest — MVP Development Plan &nbsp;&nbsp;|&nbsp;&nbsp; Confidential</div>"

## stylesheet: https://fonts.googleapis.com/css2?family=Fraunces:opsz,wght@9..144,400;9..144,600;9..144,700&family=Hanken+Grotesk:wght@300;400;500;600&display=swap

<style>
  body { font-family: 'Hanken Grotesk', sans-serif; color: #2A241E; line-height: 1.6; font-size: 12.5px; }
  h1, h2, h3, h4 { font-family: 'Fraunces', serif; color: #14543F; }
  h1 { font-size: 30px; margin-bottom: 2px; }
  h2 { font-size: 18px; border-bottom: 2px solid #E6DBCB; padding-bottom: 6px; margin-top: 28px; }
  h3 { font-size: 14px; color: #C0673E; margin-top: 18px; margin-bottom: 6px; }
  h4 { font-size: 13px; color: #14543F; margin-top: 12px; margin-bottom: 4px; }
  table { font-size: 11.5px; border-collapse: collapse; width: 100%; margin: 12px 0; }
  th { background-color: #14543F; color: white; padding: 7px 10px; text-align: left; font-weight: 500; }
  td { padding: 7px 10px; border-bottom: 1px solid #E6DBCB; vertical-align: top; }
  tr:nth-child(even) { background-color: #FBF6EE; }
  .subtitle { font-size: 15px; color: #C0673E; font-weight: 500; margin-bottom: 18px; }
  .lead { font-size: 13.5px; line-height: 1.7; color: #3d362e; }
  .callout { background-color: #FBF6EE; border-left: 4px solid #14543F; padding: 12px 16px; margin: 16px 0; border-radius: 0 6px 6px 0; }
  .callout p { margin: 4px 0; }
  .warn { background-color: #fbf0ea; border-left: 4px solid #C0673E; padding: 12px 16px; margin: 16px 0; border-radius: 0 6px 6px 0; }
  .warn p { margin: 4px 0; }
  .highlight-box { background-color: #14543F; color: white; padding: 16px 20px; border-radius: 6px; margin: 18px 0; }
  .highlight-box p { margin: 4px 0; color: white; }
  .highlight-box strong { color: #e8d5b7; }
  strong { color: #14543F; }
  hr { border: none; border-top: 1px solid #E6DBCB; margin: 24px 0; }
  ul { padding-left: 20px; }
  li { margin-bottom: 5px; }
  .page-break { page-break-before: always; }
  code { background: #f0e9dd; padding: 1px 5px; border-radius: 3px; font-size: 11px; }
</style>

# MVP Development Plan

<div class="subtitle">From zero to an owner-testable booking platform in 30 days</div>

<p class="lead">Goal: a working, quality direct-booking site that a handful of owner friends can use end-to-end within one month — direct bookings, calendar sync, damage deposits, and the hooks for guest screening and damage coverage — built on a stack that scales to thousands of owners without a rewrite.</p>

## The One Decision That Makes a Month Possible

<div class="highlight-box">
<p><strong>Run the friends test in Stripe TEST mode.</strong></p>
<p>Your friends complete real, full bookings — pick dates, sign the agreement, "pay" with Stripe test cards, see the deposit held and released. But no real money moves, no real identity verification is required, and you take on zero fund-custody or compliance risk during the test.</p>
<p>This pulls the three slowest, riskiest items — KYC onboarding, real escrow custody, and legal exposure — off the critical path. You flip to live money in a deliberate <strong>pilot</strong> step after the test, once the flow is proven.</p>
</div>

Everything below is scoped to get to that test. The full vision (public mode, property verification, guest CRM, referrals) comes after.

## The Stack — and Why It's the Right Bet

These are the tools from the project's tech decisions. Each was chosen because it is AI-friendly (excellent docs, huge training footprint, so Claude Code can scaffold it fast) and scalable (the same code that serves 5 owners serves 5,000).

| Layer | Tool | Why it wins for an AI-built MVP |
| --- | --- | --- |
| Framework | Next.js (App Router) | The most AI-codegen-friendly web framework; one codebase for site + API |
| Hosting | Vercel | Push to GitHub → deployed. Zero DevOps. Cron jobs built in for calendar sync |
| Database + Auth + Storage | Supabase | Postgres + auth + file storage in one. Row-level security. Scales to millions of rows |
| Payments + Escrow | Stripe Connect (Custom) | Delayed payouts = escrow. Deposit holds. Owner KYC handled by Stripe, not us |
| Email | Resend | Clean API, AI-friendly templates, generous free tier |
| Calendar sync | iCal (.ics) | Standard. Works with Airbnb/VRBO/Booking.com with no per-platform dev |
| E-signature | DocuSeal | Open-source rental agreements; self-host free or cloud |
| Screening / Coverage | Truvi (Superhog) | US + Mexico support; integrated post-test (needs a partnership agreement) |
| AI development | Claude Code | Builds and iterates the whole stack from this plan |

<div class="callout">
<p><strong>Accelerator:</strong> don't start from a blank page. Begin from a Next.js + Supabase + Stripe SaaS starter template, then have Claude Code reshape it to the booking domain. This saves roughly a week of auth/billing boilerplate.</p>
</div>

<div class="page-break"></div>

## What's Real vs. Stubbed for the Test

Being honest about this is what keeps the timeline real and the quality high.

| Capability | In the 30-day test | The honest reason |
| --- | --- | --- |
| Direct booking flow | Fully real | This is the whole point |
| Calendar sync (inbound iCal) | Fully real | Core to avoiding double-bookings |
| Calendar export (outbound .ics) | Real | Cheap to add; one endpoint |
| Payments + escrow | Real, in test mode | Stripe test mode proves the flow without fund custody |
| Damage deposit | Real, in test mode | Stripe authorization hold or held charge |
| Rental agreement | Fully real | DocuSeal works the same in test |
| Automated emails | Fully real | Resend works the same in test |
| Guest screening (Truvi) | Designed + feature-flagged; sandbox only | Truvi needs a signed partnership + onboarding call — won't be live in 30 days. We build the integration point and turn it on later |
| Damage coverage (insurance) | Stripe deposit stands in; real coverage deferred | Third-party damage underwriting requires a commercial contract. The deposit-hold mechanic is the test stand-in |
| Owner identity KYC | Skipped in test mode; built for pilot | Not needed when no real money moves |
| Public mode / property verification | Deferred | Friends = trusted-guest mode only |

## Cost to Run the Test Month

With test mode + free tiers, the platform itself is effectively free. Your only real spend is the AI subscription that builds it, plus the domain if you don't already own it.

| Item | Test-month cost | Notes |
| --- | --- | --- |
| Vercel (Hobby tier) | $0 | Free for the test; upgrade to Pro ($20/mo) at the live pilot |
| Supabase (Free tier) | $0 | 500 MB DB + 1 GB storage — plenty for a handful of owners |
| Stripe (test mode) | $0 | No charges in test mode |
| Resend (Free tier) | $0 | 3,000 emails/mo |
| DocuSeal (self-hosted or free) | $0 | Self-host on Supabase/Railway, or open-source instance |
| Monitoring (Sentry free) | $0 | Error tracking |
| GitHub | $0 | Already set up |
| Domain (famguest.com) | ~$0–$12/yr | Likely already owned |
| Claude Code (the builder) | $20–$100 | Pro at $20/mo for light use; Max 5× at $100/mo for a full month of heavy building (recommended) |
| Total out of pocket | ≈ $20–$112 | Essentially just the AI subscription |

<div class="warn">
<p><strong>Reality check on "scalable but free":</strong> the free tiers are real and generous, but the moment you go live with real money and real owners, plan on the baseline below. Nothing about the code changes — you're just upgrading plan tiers.</p>
</div>

### Baseline once live (post-test, real operations)

| Item | Monthly | Trigger to upgrade |
| --- | --- | --- |
| Vercel Pro | $20 | Custom domain on commercial use, cron limits |
| Supabase Pro | $25 | >500 MB data, daily backups, no project pausing |
| Resend Pro | $20 | >3,000 emails/mo |
| DocuSeal Cloud (or self-host $0) | $0–$20 | Convenience vs. maintenance |
| Monitoring | $0 | Free tier holds for a long time |
| Baseline total | ≈ $65–$85/mo | Matches the Year-1 infrastructure line in the financial model |

Plus per-transaction: Stripe ~2.9% + $0.30 per booking (passed to owners), and Truvi ~$4–5 per screened booking (passed to guests as the $5 add-on) once that partnership is live.

<div class="page-break"></div>

## The 30-Day Build Plan

A four-week sprint, each week ending in something demonstrable. Claude Code does the building; you steer, review, and test as the product manager.

### Week 0 — Foundation (2–3 days, runs into Week 1)

- Scaffold Next.js + Supabase + Stripe from a SaaS starter template

- Wire up GitHub → Vercel auto-deploy (staging + production)

- Define the database schema: owners, properties, listings, guests, bookings, agreements, calendar_feeds, deposits

- Set up Supabase Auth (email magic links — no passwords)

- Apply brand design tokens (Fraunces / Hanken Grotesk, the green/terracotta/cream palette)

Deliverable: a deployed, branded skeleton with login that you can visit at a URL.

### Week 1 — Owner Onboarding & Listings

- Owner signup + dashboard

- Property/listing creation form

- Photo upload (drag-and-drop + mobile; cloud OAuth deferred to post-test)

- AI-written description (owner pastes their text or answers prompts → Claude API polishes)

- Stripe Connect account creation wired in (test mode — KYC stubbed)

Deliverable: an owner can create an account and publish a listing with photos and a description.

### Week 2 — Calendar Sync & Booking Page

- Inbound iCal: owner pastes Airbnb/VRBO export URLs; Vercel Cron refreshes every 15–30 min; availability merged

- Outbound .ics: unique export URL per listing

- "Last synced" timestamp shown to set expectations

- Guest-facing booking page — branded to the property, mobile-first, no guest account required

- Date selection against live availability + transparent price breakdown

Deliverable: a guest can open an owner's link and see real availability and pricing.

### Week 3 — Payments, Deposits & Agreements

- Stripe payment flow (test mode) with escrow via delayed payout

- Damage deposit as a separate authorization hold / held charge, with release after the inspection window

- DocuSeal rental agreement auto-generated per booking; guest signs before payment confirms

- Booking confirmation + state machine (pending → agreement signed → paid → confirmed)

Deliverable: a complete booking — dates → agreement → payment → deposit hold → confirmation — works end to end.

### Week 4 — Messaging, Screening Hooks & Polish

- Resend automated emails: confirmation, pre-arrival, check-in instructions, checkout, deposit release

- Digital house manual (private link)

- Guest screening / damage coverage: build the feature-flagged integration points (Truvi sandbox); show the $5 screening and $19.99 protected-booking options in the UI even if backed by sandbox during the test

- Error handling, friendly messages, mobile QA, accessibility pass

- Seed 2–3 real owner listings; recruit the friend testers

Deliverable: the full owner + guest experience, ready for friends to test.

## Pre-Test Checklist

- Staging and production environments both deploy cleanly from main

- All secrets in Vercel env vars; nothing committed (.env.example documented)

- Stripe in test mode; test card numbers documented for testers

- At least 2 real owner listings live with photos and calendars synced

- One full booking completed by you, start to finish, before any friend touches it

- A short "how to test" guide for your owner friends (with test card numbers)

- Feedback capture (a simple form or shared doc) ready

## What Comes After the Test

The test answers one question: is this easy and trustworthy enough that owners would actually send their guests the link? Once you have that:

- Live pilot — flip Stripe to live mode, turn on real owner KYC (Connect Custom), upgrade to paid tiers, run a small number of real-money bookings with the most enthusiastic testers.

- Sign the Truvi partnership — turn guest screening and damage coverage from sandbox to real (this can run in parallel during the test month).

- Safety-critical review — spend the budgeted $5,000 on a contract engineer to review Stripe webhooks, escrow timing, and security hardening before scaling.

- Guest CRM & rebooking — build the retention moat (re-invite, one-click rebook, referrals).

- Public mode — property verification + open listings, once trusted-guest retention is proven.

<div class="callout">
<p><strong>Bottom line:</strong> you can have owner friends testing a genuinely good product in 30 days for the cost of one AI subscription — roughly <strong>$20–$100</strong> — on infrastructure that scales straight through to the Year-3 numbers in the business plan, with no rewrite.</p>
</div>

<div style="text-align: center; margin-top: 28px; color: #8a7e72; font-size: 11px;">
famguest.com &nbsp;&nbsp;|&nbsp;&nbsp; June 2026
</div>